## Meridian
City of Meridian 2021 Prioritization Request Form
Updates include draft FY2021-2025 IFYWP. Programming status is subject to change.
Ranking Instructions:
1. Rank your project request using only one number per project (Please avoid using 2a, 2b, 2c, etc.).
2. Utilize the first column to reevaluate your prioritization ranking. Adjust as needed.
3. Blank lines are provided at the end of each category to add additional projects. Provide a clear description of the project request.
4. Remember to identify projects for removal.
2021 Priority Ranking | 2020 Priority Ranking | Agency Project Name | Agency Project Description | Current IFYWP Programming Status |  |  | ACHD Response | ACHD Implementation Project Name
|  |  |  | Design YR | ROW YR | Construction YR
Roads & Intersections
1 | 2 | Linder Rd, Overland Rd / Franklin Rd | Widen Linder Rd to 5 lanes and construct a new 4-lane 1-84 overpass, including curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. Project would be a joint project between ACHD and ITD | Future | Future | Future | Project added to IFYWP for discussion purposes. ACHD to coordinate with ITD on request. Project to move forward when funding partnership is possible. | Linder Rd, Overland Rd / Franklin Rd
2 | 1 | Locust Grove Rd, Victory Rd / Overland Rd | Widen Locust Grove Rd to 5 lanes with curb, gutter, sidewalk and bike lanes in accordance with the 2016 CIP. | 2019 | 2020-2021 | 2022 | Project to be built in 2022. | Locust Grove Rd, Victory Rd / Overland Rd
3 | 3 | Locust Grove Rd, Fairview Ave / Ustick Rd | Widen Locust Grove Rd to 5 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Per City request, ACHD to coordinate with Meridian to discuss scope. | Locust Grove Rd, Fairview Ave / Ustick Rd
4 | 4 | Fairview Ave and Locust Grove Rd | Widen intersection to 9 lanes on Fairview Ave and 7 lanes on Locust Grove Rd, including curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2020-2021 | 2021-2022 | 2023 | Project to be built in 2023. | Fairview Ave and Locust Grove Rd
5 | 6 | Ten Mile Rd, Victory Rd / Overland Rd | Widen Ten Mile Rd to 5 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2019 | 2020-2021 | 2022-2023 | Project to be built in 2022-2023. | Ten Mile Rd, Victory Rd / Overland Rd
6 | 7 | Victory Rd, Locust Grove Rd / Eagle Rd | Widen Victory Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2023 | 2024 | Future | Project to begin design in 2023. | Victory Rd, Locust Grove Rd / Eagle Rd
7 | 8 | Ustick Rd, Ten Mile Rd / Linder Rd | Widen Ustick Rd to 5 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2022 | 2023 | 2025 | Project to be built in 2025. | Ustick Rd, Ten Mile Rd / Linder Rd
8 | 9 | Linder Rd, Cherry Ln / Ustick Rd | Widen Linder Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with 2016 CIP. | 2025 | Future | Future | Project to begin design in 2025. | Linder Rd, Cherry Ln / Ustick Rd
9 | 10 | Locust Grove Rd, Amity Rd / Victory Rd | Widen Locust Grove Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Locust Grove Rd, Amity Rd / Victory Rd
10 | 11 | Victory Rd, Meridian Rd / Locust Grove Rd | Widen Victory Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2023 | 2024 | 2025 | Project to be built in 2025. | Victory Rd, SH 69 (Meridian Rd) / Locust Grove Rd
11 | 12 | Ten Mile Rd / Cherry Ln | Intersection improvements to include dual left turn lanes. | 2025 | Future | Future | Project to begin design in 2025. | Ten Mile Rd and Cherry Ln
12 | 13 | Eagle Rd / Overland Rd | Intersection improvements to include dual left turn lanes. | 2025 | Future | Future | Project to begin design in 2025. | Overland Rd and Eagle Rd
13 | 14 | McMillan Rd, Meridian Rd / Locust Grove Rd | Widen McMillan Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | McMillan Rd, SH 69 (Meridian Rd) / Locust Grove Rd
14 | 15 | McMillan Rd, Linder Rd / Meridian Rd | Widen McMillan Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | McMillan Rd, Linder Rd / SH 69 (Meridian Rd)
15 | 16 | Victory Rd and Locust Grove Rd Roundabout | Construct a multi-lane roundabout with 2 lanes on Locust Grove legs and 1 lane on Victory legs in accordance with the 2016 CIP. | 2019 | 2020-2021 | 2022-2023 | Project to be built in 2022-2023. | Victory Rd and Locust Grove Rd Roundabout
16 | 19 | Locust Grove Rd, Ustick Rd / McMillan Rd | Widen Locust Grove Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Locust Grove Rd, Ustick Rd / McMillan Rd
17 | 20 | Meridian Rd, Ustick Rd / McMillan Rd | Widen Meridian Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2023 | 2024 | Future | Project to begin design in 2023. | Meridian Rd, Ustick Rd / McMillan Rd
18 | 23 | Ustick Rd and Black Cat Rd | Construct a dual lane roundabout in accordance with the 2016 CIP. | Not Programmed | Not Programmed | 2021 | Interim Signal to be constructed in 2021. | Ustick Rd and Black Cat Rd
19 | 24 | Ustick, Black Cat to Ten Mile | Widen to 5 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Ustick Rd, Black Cat Rd / Ten Mile Rd
20 | NEW | Lake Hazel, Locust Grove to Eagle | Widen and improve pedestrian facilities. Some segments are already planned for improvement; having the full block complete would provide better connections to adjacent development and amenities.
21 | 18 | Meridian Rd, McMillan Rd / Chinden Blvd | Widen Meridian Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2023 | 2024 | Future | Project to begin design in 2023. | Meridian Rd, McMillan Rd / US 20/26 (Chinden Blvd)
22 | 21 | Lake Hazel Rd and Eagle Rd | Widen and signalize intersection to 4/5 lanes on Eagle and 315 lanes on Lake in accordance with the 2016 CIP. | 2020 | 2021-2022 | 2022 | Project to be built in 2022. | Lake Hazel Rd and Eagle Rd
23 | 22 | Overland Rd and Linder Rd | Widen and signalize intersection to 5 lanes on Linder Rd and 6 lanes on Overland Rd in accordance with the 2016 CIP . | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Overland Rd and Linder Rd
24 | 25 | Victory, Linder to Meridian | Widen to 3 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Victory Rd, Linder Rd / SH 69 (Meridian Rd)
25 | 27 | Franklin Rd, McDermott Rd / Black Cat Rd | Widen Franklin Rd to 5 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Franklin Rd, McDermott Rd / Black Cat Rd
26 | 28 | Eagle Rd / Franklin Rd | Not provided | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Eagle Rd and Franklin Rd
27 | 30 | Cherry Ln and Linder Rd | Widen intersection to 4 lanes Linder Rd and 5/6 lanes on Cherry Ln in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Cherry Ln and Linder Rd
28 | 31 | Cherry Ln and Black Cat Rd | Widen intersection to 5/6 lanes on Black Cat Rd and 5 lanes on Cherry Ln in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Cherry Ln and Black Cat Rd
29 | 32 | Fairview Ave, SH 55 (Eagle Rd) / Cloverdale Rd | Widen Fairview Ave to 7 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Fairview Ave, SH 55 (Eagle Rd) / Cloverdale Rd
30 | 33 | Linder Rd, Chinden Blvd (US 20/26) / SH 44 (State St) | Widen Linder Rd in accordance with the 2016 CIP. Cross section to be determined through concept design. Project includes bridges #1078, #2033, #2034, #2035, and #2036. | 2024-2025 | Future | Future | Project to begin design in 2024-2025. | Linder Rd, Chinden Blvd (US 20/26) / SH 44 (State St)
31 | 34 | Fairview Ave, Locust Grove Rd / SH 55 (Eagle Rd) | Widen Fairview Ave to 7 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | 2020-2021 | 2021-2022 | 2023 | Project to be built in 2023. | Fairview Ave, Locust Grove Rd / SH 55 (Eagle Rd)
32 | 35 | Fairview Ave, Meridian Rd / Locust Grove Rd | Widen Fairview Ave to 7 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Fairview Ave, Meridian Rd / Locust Grove Rd
33 | 36 | Cherry Ln, Linder Rd / Meridian Rd | Widen Cherry Ln to 5 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Cherry Ln, Linder Rd / Meridian Rd
34 | 37 | Fairview Ave Corridor Management, Linder Rd / Orchard St | Improve safety and traffic operations along Fairview Ave in accordance with the Fairview Avenue Corridor Management Strategy. Project may include bicycle and pedestrian facilities and other access management treatments. | Not Programmed | Not Programmed | Not Programmed | Project to be implemented through development. ACHD and Meridian to coordinate implementation as development applications are processed. | Fairview Ave Corridor Management, Linder Rd / Orchard St
35 | 17 | Ten Mile Rd and Victory Rd | Widen intersection or add roundabout in accordance with the Master Street Map. Traffic analysis should determine the ultimate lane configuration based on above projects in the area. | 2019-2020 | 2020-2021 | 2022-2023 | Project to be built in 2022-2023. | Ten Mile Rd and Victory Rd
36 | 29 | Ten Mile Rd and Amity Rd | Construct a roundabout. Project includes bridge #205AX. | 2018 | 2019-2020 | 2021 | Project to be built in 2021. | Ten Mile Rd and Amity Rd
37 | 38 | Ten Mile Rd, Amity Rd / Victory Rd | Widen Ten Mile Rd to 5 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Ten Mile Rd, Amity Rd / Victory Rd
38 | 39 | East 03rd St Extension, Carlton St / Fairview Ave (Phase 2) | Extend roadway and construct streetscape improvements, including curb, gutter, sidewalk, and improved UPRR crossing, from Carlton Ave to Fairview Ave in accordance with the Downtown Meridian Neighborhood Plan. | Not Programmed | Not Programmed | Not Programmed | Defer until completion of Phase 1 (Franklin to Carlton). | East 03rd St, Carlton St / Fairview Ave (Phase 2)
39 | 40 | Broadway Ave / Idaho Ave Extension, East 06th St / Locust Grove Rd | Not provided | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Broadway Ave / Idaho Ave Extension, 06th St / Locust Grove Rd
40 | 41 | McMillan Rd and Black Cat Rd | Construct a multi-lane roundabout in accordance with the 2016 CIP . | Not Programmed | Not Programmed | 2021 | Interim Signal to be constructed in 2022. | McMillan Rd and Black Cat Rd
41 | 42 | Amity Rd and Black Cat Rd | Widen intersection to 3/4 lanes on Amity and 314 lanes on Black Cat in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Amity Rd and Black Cat Rd
42 | 43 | McMillan Rd and Star Rd | Construct a multi-lane roundabout in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | McMillan Rd and Star Rd
43 | 44 | Amity Rd and Linder Rd | Construct a single-lane roundabout in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Amity Rd and Linder Rd
44 | 45 | Cherry Ln and McDermott Rd | Widen intersection to 3 lanes on McDermott and 5 lanes on Cherry. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Cherry Ln and McDermott Rd
45 | 46 | Franklin Rd and McDermott Rd | Construct a single-lane roundabout in accordance with the 2016 CIP. | 2024 | 2025 | Future | Project to begin design in 2024. | Franklin Rd and McDermott Rd
46 | 47 | Ustick Rd and McDermott Rd | Widen intersection to 3 lanes on McDermott and 4 lanes on Ustick in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Ustick Rd and McDermott Rd
47 | 48 | McMillan Rd and McDermott Rd | Widen and signalize intersection to 3/4 lanes on McDermott and 3 lanes on in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | McMillan Rd and McDermott Rd
48 | 49 | Ustick Rd and Star Rd | Construct a single-lane roundabout in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Ustick Rd and Star Rd
49 | 50 | Ten Mile Rd and Chateau Dr | Signalize intersection. | Not Programmed | Not Programmed | Not Programmed | Does not currently meet warrants. ACHD to reevaluate as development occurs in the area. | Ten Mile Rd and Chateau Dr
50 | 51 | Lake Hazel Rd and Locust Grove Rd | Construct a single-lane roundabout in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Lake Hazel Rd and Locust Grove Rd
51 | 52 | Amity Rd and Locust Grove Rd | Widen and signalize intersection to 3/4 lanes on Locust Grove and 5/6 lanes on Amity in accordance with the 2016 CIP . | Not Programmed | Not Programmed | 2023 | Interim signal to be constructed in 2023. | Amity Rd and Locust Grove Rd
52 | 53 | Victory Rd and Linder Rd | Construct a single-lane roundabout in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Victory Rd and Linder Rd
53 | 54 | Locust Grove Rd, McMillan Rd / Chinden Blvd (US 20/26) | Widen Locust Grove Rd to 3 lanes with curb, gutter, sidewalk, and bike lanes in accordance with the 2016 CIP. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Locust Grove Rd, McMillan Rd / US 20/26 (Chinden Blvd)
54 | 55 | Ustick Rd, McDermott Rd / Black Cat Rd | Widen Ustick Rd to 5 lanes with curb, gutter, sidewalk, and bike lanes. | Not Programmed | Not Programmed | Not Programmed | Defer. Operating at a LOS D or better. Reevaluate as conditions change. | Ustick Rd, McDermott Rd / Black Cat Rd
55 | 56 | Pine, Linder to Meridian | Widen to 3 lanes with curb, gutter, sidewalks and/or multi-use or mixed-use bikeway. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Pine Ave, Linder Rd / Meridian Rd
56 | 57 | Eagle Rd / Fairview Ave | Not provided | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Eagle Rd and Fairview Ave
57 | 58 | Lake Hazel / Discovery Park | Intersection improvements requested at entrance to Discovery Park. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Lake Hazel Rd and Discovery Park
58 | 59 | Amity, Eagle to Cloverdale | Widen to 5 lanes with curb, gutter, sidewalk, and bike lanes. TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Amity Rd, Eagle Rd / Cloverdale Rd.
59 | 60 | Amity, Locust Grove to Eagle | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Amity Rd, Locust Grove Rd / Eagle Rd
60 | 61 | Victory, Ten Mile to Linder | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Victory Rd, Ten Mile Rd / Linder Rd
61 | 62 | Black Cat, Cherry to Ustick | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Blact Cat Rd, Cherry Ln / Ustick Rd
62 | 63 | Black Cat, Franklin to Cherry | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Blact Cat Rd, Franklin Rd / Cherry Ln
63 | 64 | Black Cat, Ustick to McMillan | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Black Cat Rd, Ustick Rd / McMillan Rd
64 | 65 | Black Cat, McMillan to Chinden | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Black Cat Rd, McMillan Rd / US 20/26 (Chinden Blvd)
65 | 66 | McMillan, Black Cat to Ten Mile | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | McMillan Rd, Black Cat Rd / Ten Mile Rd
66 | 67 | McMillan, Ten Mile to Linder | TBD | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | McMillan Rd, Ten Mile Rd / Linder Rd
67 | 68 | Eagle, Lake Hazel to Amity | TBD | 2021 | 2022 | 2023 | Project to be built in 2023. | Eagle Rd, Lake Hazel Rd / Amity Rd
68 | 69 | Locust Grove, Lake Hazel to Amity | TBD. 3-lane? | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Locust Grove Rd, Lake Hazel Rd / Amity Rd
69 | 26 | Eagle Rd and Amity Rd Roundabout (Dual Lane) | Widen roundabout to a dual lane roundabout, with curb, gutter, sidewalk, and bike lanes. Project to be constructed concurrently with Eagle Rd, Amity Rd / Victory Rd. | 2020 | 2020 | 2021-2022 | Project to be built in 2021-2022. | Eagle Rd and Amity Rd Roundabout (Dual Lane)
70 | 5 | Eagle Rd, Amity Rd / Victory Rd | Widen Eagle Rd to 5 lanes with curb, gutter, sidewalk and bike lanes in accordance with the 2016 CIP. | 2018 | 2019-2020 | 2021-2022 | Project to be built in 2021-2022. | Eagle Rd, Amity Rd / Victory Rd
Community Programs
1 | 6 | Stockenham Enhanced Cross-walks | Remove mid-block cross-walk by Hillsdale and add enhanced cross-walks at Lachlan and near Rockhampton/Hill Park St. Update school zone signs and flashers. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Hillsdale Elementary Pedestrian Crossings and School Zone
2 | 2 | Stoddard Rd, Victory Rd / Overland Rd (Stoddard Rd, Victory Rd / Kodiak Dr) | Reconstruct Stoddard Rd, between Victory Rd and Overland Rd to 3-lanes, 7' attached sidewalks and bike lanes. Project includes bridge #2085 and an enhanced pedestrian crossing (pedestrian hybrid beacon) at Victory and Stoddard (CM214-27). Bike lanes may be replaced by a pathway per the Bike Master Plan Update. | 2022 | 2023 | 2024 | Project to be built in 2024. | Stoddard Rd, Victory Rd / Overland Rd
3 | 3 | East 03rd St, Franklin Rd / Carlton Ave (Phase 1) | Construct streetscape improvements, including curb, gutter, sidewalk, and improved UPRR crossing, from Franklin Rd to Carlton Ave in accordance with the Downtown Meridian Neighborhood Plan. | 2022 | 2023 | 2025 | Projects to be built in 2025. | East 03rd St, Franklin Rd / Carlton St
4 | 14 | E. 3rd Carlton to Fairview | Extend roadway and construct streetscape improvements, including curb, gutter, sidewalk, and improved UPRR crossing, from Carlton Ave to Fairview Ave in accordance with the Downtown Meridian Neighborhood Plan. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | East 03rd St, Carlton St / Fairview Ave (Phase 2)
5 | 15 | Washington St, W. 07th St / Main St | Complete sidewalk on Washington St, between W. 07th Stand Main St. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Washington St, 07th St / Main St
6 | 4 | Broadway Ave, West 07th St / West 04th St | Complete sidewalks on the south side of Broadway Ave, between West 07th St and West 04th St. | 2024 | 2025 | Future | Project to begin design in 2024. | Broadway Ave, West 08th St / West 04th St
7 | 5 | McMillan Rd, Ten Mile Rd / Linder Rd | Install extruded curb pathway on north side of McMillan Rd between Cortona Way and Goddard Creek Way and detached concrete sidewalk with curbing between Goddard Creek Way and Wild Goose Way. | 2024 | 2025 | Future | Project to begin design in 2024. | McMillan Rd, Ten Mile Rd / Linder Rd
8 | 7 | East 2 1/2 St, Carlton Ave / Fairview Ave | Install sidewalk on the west and/or east side. | 2024 | 2025 | Future | Project to begin design in 2024. | 02nd 1/2 St, Carlton Ave / Fairview Ave
9 | 9 | Main St and King Street Pedestrian Crossing | Install an enhanced pedestrian crossing of Main St at King Street. | 2024 | 2024 | 2025 | Project to be built in 2025. | Main St and Williams St Pedestrian Crossing
10 | 37 | Amity, Eagle to Hillsdale | Pedestrian improvements on Amity to the YMCA and City Park. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Amity Rd, Eagle Rd / Cloverdale Rd.
11 | NEW | Amity, Meridian to Locust Grove | pedestrian improvements
12 | 20 | Bower St, Meridian Rd / E. 03rd St | Complete sidewalks and add wayfinding signage on Bower St, between Meridian Rd and E. 03rd St. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Bower St, Meridian Rd / 03rd St
13 | 24 | Victory Rd, Glacier Bay Way / Mesa Way | Complete sidewalk on the south side adjacent to county parcel. | 2023 | 2024 | 2025 | Project to be built in 2025. | Victory Rd, SH 69 (Meridian Rd) / Locust Grove Rd
14 | 8 | Capulet Way at Siena Elementary | Install crosswalk of Capulet Way on the west side of Siena Elementary school micro path. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Capulet Way Pedestrian Crossing (S/O Falcon Dr)
15 | 30 | Taormina Drive at Maesaia Way | Install sidewalk on south side of Taormina Drive near Maesaia Way. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Taormina Dr at Maesaia Way
16 | 16 | Taconic Dr / Pioneer | Install crosswalk at intersection of Taconic and Pioneer (Hillsdale Subdivision). | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Taconic Dr and Pioneer Trail Ave Pedestrian Crossing
17 | NEW | Lake Hazel Rd, Locust Grove to Eagle | Complete the pedestrian improvements along the full mile. Some segments are already planned for improvement, but when they are complete there will still be gaps to the north and south.
18 | 1 | Locust Grove Rd, Overland Rd / Puffin St | Construct a detached asphalt or concrete pathway on east side of Locust Grove between Puffin Stand Overland Rd. | 2019 | 2020-2021 | 2022 | Project to be built in 2022. | Locust Grove Rd, Victory Rd / Overland Rd
19 | 18 | Pine Ave and W. 1st St Pedestrian Crossing | Install an enhanced pedestrian crossing (rectangular rapid flashing beacon) on Pine Ave at W 01st St to improve access to Meridian Elementary School. | 2025 | 2025 | Future | Project to begin design in 2025. | Pine Ave and 01st St Pedestrian Crossing
20 | 21 | McMillan Rd, Locust Grove Rd / Red Horse Way | Complete sidewalk on the north side of McMillan Rd, between Locust Grove Rd and Red Horse Way. | 2024 | 2025 | Future | Project to begin design in 2024. | McMillan Rd, Red Horse Way / Locust Grove Rd
21 | 23 | Linder Rd, Washington St / Maple St | Complete sidewalk on the west side of Linder Rd, between Washington St and Maple St. | Not Programmed | Not Programmed | Not Programmed | Complete pedestrian facilities existing in this section. | Linder Rd, Washington St / Maple St
22 | 25 | Locust Grove Rd and Palermo Dr Pedestrian Signal | Install an enhanced pedestrian signal and lighting on the north side of Palermo at Locust Grove. | 2022 | 2022 | 2023 | Project to be built in 2023. | Locust Grove Rd and Palermo Dr Pedestrian Crossing
23 | 27 | Meridian, north of Ustick | Install an enhanced pedestrian crossing of Meridian Rd at/near Settlers Park entrance and Sundance Subdivision micropath. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Meridian Rd Pedestrian Crossings (Settlers Park Entrance / Sundance Sub Micropath)
24 | 29 | Locust Grove Rd and Time Zone Dr Pedestrian Crossing | Install an enhanced pedestrian crossing of Locust Grove Rd at Time Zone Dr. | 2019 | 2020-2021 | 2022 | Project to be built in 2022. | Locust Grove Rd, Victory Rd / Overland Rd
25 | 35 | Bridgetower Pedestrian Signal | Pedestrian signal on Ustick Road at Bridgetower (Towerbridge?) Drive. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Ustick Rd and Towerbridge Way Pedestrian Crossing
26 | NEW | Black Cat-Ten Mile Bikeway, Cherry Lane / Ustick Road | Install Level 1 bike facilities along the Black Cat-Ten Mike Bikeway
27 | NEW | Central Meridian Bikeway, Blue Heron Street / Chinden Boulevard | Install Level 1 bike facilities along the Central Meridian Bikeway from Blue Heron Street to Chinden Boulevard
28 | NEW | Chinden-McMillan Bikeway, Ten Mile Road / Sedona Drive | Install Level 1 and Level 3 bike facilities along the Chinden-McMillan Bikeway from Ten Mile Road to Sedona Drive
29 | NEW | Gondola-Malta Bikeway, Black Cat Road / Goddard Creek Way | Install Level 1 and Level 3 bike facilities
30 | NEW | Granger Avenue Bikeway, Records Avenue / Cloverdale Road | Install Level 1 bike facilities
31 | NEW | Linder Road, Maple Avenue / Cherry Lane | Install Level 3 bike facilities
32 | NEW | Linder-Meridian Bikeway, Cherry Lane / Chinden Boulevard | Install Level 1 and Level 3 bike facilities
33 | NEW | Locust Grove Road, Leighfield Drive to Star Lane | Connect gap from existing sidewalk on west side of Locust Grove Road, along with improving narrow sidewalk on east side of roadway.
34 | NEW | Locust Grove-Eagle Bikeway, Pine Avenue / McMillan Road | Install Level 1 and Level 3 bike facilities
35 | NEW | Locust Grove Road and Heritage Park Street | Install an enhanced crossing (pedestrian hybrid beacon) on Locust Grove Road at Heritage Park Street, access for Meridian Technical Charter High School
36 | NEW | Locust Grove Rd, Paradise Ln / Grand Canyon Dr | Install sidewalks on the east side of Locust Grove Rd to connect with an existing path to the school.
37 | NEW | McMillan-Ustick Bikeway, Cool River Avenue / Eagle Road | Install Level 1 bike facilities
38 | NEW | Records Avenue, Florence Drive / Fairview Avenue | Install Level 2 bike facilities with construction ot improved roadway
39 | NEW | Records Way Bikeway, Pine Avenue / Fernside Drive | Install Level 1 bike facilities along the Records Way Bikeway from Pine Avenue to Florence Drive, Level 2 bike facilities from to Ustick Road to Baldcypress Street, and Level 1 bike facilities from Baldcypress Street to Wainwright Drive
40 | NEW | Ten Mile-Linder Bikeway, Linder Road / Chinden Boulevard | Install signing and pavement marking to existing Level 1 and Level 3 bike facilities
41 | NEW | Ustick-Cherry Bikeway, Black Cat Road / Chateau Drive | Install Level 1 bike facilities
42 | NEW | Ustick Road and Venable Lane | Install an enhanced crossing (pedestrian hybrid beacon)
43 | 10 | McMillan Rd and Palantine Way Pedestrian Crossing | Install an enhanced pedestrian crossing and curb ramps on McMillan Rd at Palantine Way. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | McMillan Rd and Palantine Way Pedestrian Crossing
44 | 11 | Meridian Rail-with-Trail | Multi-use pathway along rail road tracks. | Not Programmed | Not Programmed | Not Programmed | ACHD to prioritize and scope arterial crossings when City moves pathway project forward. | Meridian Rail-with-Trail
45 | 12 | Locust Grove Rd and Woodbridge Dr Pedestrian Crossing | Install an enhanced pedestrian crossing of Locust Grove Rd at Woodbridge Dr or Watertower St. | 2023 | 2023 | 2024 | Project to be built in 2024. | Locust Grove Rd and Woodbridge Dr Pedestrian Crossing
46 | 13 | Eagle Rd, River Valley St / Ustick Rd | Complete sidewalks on Eagle Rd, between River Valley Stand Ustick Rd. | Not Programmed | Not Programmed | Not Programmed | ITD facility. ACHD to share request with ITD. | Eagle Rd, River Valley St / Ustick Rd
47 | 19 | Washington St and W 1st St Pedestrian Crossing | Pedestrian crossing near Meridian Elementary School. | Not Programmed | Not Programmed | Not Programmed | Evaluation completed fall 2016 shows existing crossing meet needs of current users. ACHD to reevaluate as conditions change. | Washington St and 01st St Pedestrian Crossing
48 | 26 | W 08th St and Meridian Middle School Pedestrian Crossing | Install an enhanced pedestrian crossing on 8th St at Meridian Middle School. | 2020 | 2020 | 2021 | Project to be built in 2021. | Enhanced School Crossings - Meridian Middle School and Capital High School
49 | 28 | Chinden Blvd, east of Ten Mile Rd | Complete sidewalks on Chinden Blvd, east of Ten Mile Rd. | Not Programmed | Not Programmed | Not Programmed | ITD facility. ACHD to share request with ITD. | Chinden Blvd, E/O Ten Mile Rd
50 | 31 | Woodbridge Neighborhood Bike Study | Study the connectivity and bikeability of the Woodbridge neighborhood. | Not Programmed | Not Programmed | Not Programmed | ACHD to evaluate as part of future budgeting efforts. | Woodbridge Neighborhood Bike Study
51 | 32 | Watertower St at Rebound School | Install a painted crosswalk on Watertower St at Rebound School. | Not Programmed | Not Programmed | Not Programmed | ACHD Traffic Engineering does not recommend installation. Crossing activity is caused by parent drop off. | Watertower St and Rebound School Pedestrian Crossing
52 | 33 | Linder Rd, Chateau Dr / Barbara Morgan STEM | Way finding signage on Linder. | Not Programmed | Not Programmed | Not Programmed | ACHD Traffic believes current signage is adequate. No additional signage recommended. | Linder Rd, Chateau Dr / Barber Morgan STEM
53 | 34 | St. Ignatius School Pedestrian Signal | Pedestrian signal on Meridian Road at Producer. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Meridian Rd and Producer Dr Pedestrian Crossing
54 | 36 | Fairview Terrace to Chief Joseph | Pedestrian connection (sidewalk) between Barbara Drive in Fairview Terrace Park to E. Willowbrook Drive and Chief Joseph Elementary on Chateau Drive. | Not Programmed | Not Programmed | Not Programmed | ACHD to support City led effort. Coonection would be located on private property. | Barbara Dr Pedestrian Connection
55 | 38 | West 02nd St, UPRR / Broadway Ave | Complete sidewalk on both sides of West 02nd, between the Union Pacific Railroad and Broadway Ave to address parking concerns in this area. | Not Programmed | Not Programmed | Not Programmed | Sidewalk scoped "No Go" in 2015. Agencies to coordinate if other solutions identified. | West 02nd, UPRR / Broadway Ave
56 | 40 | Kentucky Ridge Way, Riodosa Dr / Victory Rd | Sidewalk on the west side of Kentucky Ridge Way, between Victory and Riodosa. | Not Programmed | Not Programmed | Not Programmed | Scoped "Go - Defer" in 2015. Sidewalk exists on the east side. ACHD to reevaluate if existing sidewalk does not meet needs in area. | Kentucky Way, Riodosa Dr / Victory Rd
57 | 41 | State Ave, East 2nd St / Cathy Ln | Sidewalk repair. Requested by land owner in this area. | Not Programmed | Not Programmed | Not Programmed | Scoped "No Go" in 2015. This section has connectivity already on the south side and the original requestor no longer owns the property. | State Ave, 2nd St / Cathy Ln
58 | 42 | Nola Rd and Crossroads Middle School Pedestrian Crossing | Install a painted crosswalk on Nola Rd at Crossroads Middle School. | Not Programmed | Not Programmed | Not Programmed | Scoped "No Go" in 2018 as issues are caused by drop-off activities. Encourage school to work with parents. | Nola Rd and Crossroads Middle School Pedestrian Crossing
59 | 43 | Nola Rd, south of Pine Ave Middle School | Construct sidewalk on the east side of Nola Rd from Pine Ave to Crossroads. | Not Programmed | Not Programmed | Not Programmed | Scoped "No Go" in 2018. Sidewalk on east side to be built through development. | Nola Rd, Pine Ave / Crossroads Middle School
60 | NEW | McDermott Road, Ustick Road to McMillan Road | Install sidewalk on the west side of McDermott Road connecting to sidewalk on Ustick Road and McMillan Road for connectivity to Owyhee High School
Removed Requests
Completed | 39 | Locust Grove Rd, Paradise Ln / Grand Canyon Dr | Asphalt path on the east side of Locust Grove Rd to connect with an existing path to the school. | Completed | Completed | Completed | Asphalt pathway with extruded curb exists on the east side of Locust Grove Rd. Project completed in 2010. | Locust Grove Rd, Paradise Ln / Grand Canyon Dr
Duplicate | 17 | Amity and Mary McPherson Elementary School Pedestrian Signal | Signalized pedestrian crossing. | Not Programmed | Not Programmed | Not Programmed | Scoped "Go - Defer" in 2017 due to low pedestrian volumes. ACHD to reevaluate as conditions change in the area. | Amity Rd and Mary McPherson Elementary School Pedestrian Crossing
Duplicate | 22 | Linder Rd, 1-84 / Franklin Rd | Complete sidewalks the west side on Linder Rd, between 1-84 and Franklin Rd. | Future | Future | Future | Project added to IFYWP for discussion purposes. ACHD to coordinate with ITD on request. Project to move forward when funding partnership is possible. | Linder Rd, Overland Rd / Franklin Rd